## Jan 2012
January 2012 Calendar. This calendar is designed for easy use as a planner and has print range preset. | [11 empty] | Made with WinCalendar: | Calendar Creator Software
| ◄ Dec 2011 |  | ~ January 2012 ~ | [6 empty] | Feb 2012 ► |  |  | 2011 XLS Calendars
| Sunday | Monday | Tuesday | Wednesday |  | Thursday |  | Friday |  | Saturday |  |  | 2012 XLS Calendars
| 2012-01-01 | 2012-01-02 | 2012-01-03 | 2012-01-04 |  | 2012-01-05 |  | 2012-01-06 |  | 2012-01-07 |  |  | XLS Calendar Templates
| Ramie sets up MySQL database connection in the class and generate stub data to test it out with. | Group gets together on skype and plans things out. | BREAK | BREAK |  | Meet again and finish the Student/Teacher/Database/Equipment classes |  | BREAK |  | Work on software scope document.
| As per planned, for the first time ever, we follow what were suppose to do. | Only 2 people showed up on skype and we got barely any work done. We just loafted our way. | Shayan tried to create the student class alone, while Amil started the teacher class. Ramie consulted us over the phone on how to complete it. | Shayan sent a text message out to everyone and reminded them we need to start the project ASAP. |  | Today was a productive day, we spent 5 hours and got all those classes done. They arent perfected though, there is still some work to do. |  | Amil finishes equipment class with the help of Ramie. Shayan is completing the student class with Moeen and Ramie. |  | Mellissa perfects the Teacher class. We still have work to do on the course class!
| 2012-01-08 | 2012-01-09 | 2012-01-10 | 2012-01-11 |  | 2012-01-12 |  | 2012-01-13 |  | 2012-01-14
| Finish Software Scope Document | *Presentation day Finish the Student class at home and get the setters and getters done | *Presentation days Amil Mellissa Shayan are to get together and complete their Student-Teacher system planning | *Presentation days Shayan and Ramie are suppose to work on the splash screen and how to embed SWF Files into C# |  | Amil and Mellissa are to complete and finalize how they will carry out the linkage between the Student and Teacher class . |  | Fire Drill
| Shayan and Amil finish the teacher class and Ramie reviews it. | Ramie works on the GUI design with Shayan and Amil | Mellissa work | Ramie revamped the database class because Student arrays took time to load. Moeen and Ramie finished the Config class |  | PEOPLE ARE STUDYING FOR A MATH TEST :) |  | LOAFT DAY: Ramie thinks we can pull this off last minute. The rest of the group agrees *BAD IDEA*
| 2012-01-15 | 2012-01-16 | 2012-01-17 | 2012-01-18 |  | 2012-01-19 |  | 2012-01-20 |  | 2012-01-21
| Amil and Shayan finished their teacher panel, radio buttons and role selection with the help of Ramie |  | Everyonefinishes up their GUI forms for their classes and make sure they look good | Everyone checks their own classes to solve bugs before finalizing |  | Everyone makes sure that all classes are complete and can be linked together |  | Moeen and Amil make sure that buttons are all working fine and no bugs pop up |  | Shayan finish the graphical art and merge it together with the project.
| Amil and Shayan finished their teacher panel, radio buttons and role selection with the help of Ramie | Mellissa got some information about the formulas that are to be used. Ramie helped mellissa with the methods to calculate marks. | Ramie started the Course class. It required a lot of formulas, array searching and sorting, as well as organized object construction | Moeen and Ramie made the Course main constructor's get and set methods. Some of them required complex formula. |  | We are falling behind a bit, Ramie has a math Test, and so does Moeen and Amil and Mellissa. We call this day off. |  | Ramie's hard drive crashes over night as he reinstalls windows, and the UPDATED work we have done is gone from his computer. |  | We have a lot of work to do, and we are rolled back by 3 hard-working days. Mellissa and Amil are workin the UML. Shayan and Moeen work on setters and getters.
| 2012-01-22 | 2012-01-23 | 2012-01-24 | 2012-01-25 |  | 2012-01-26 |  | 2012-01-27 |  | 2012-01-28
| Double check everything and see if the program works fine. Finish all the commenting to ensure this is a perfect product. | Submit the Project with a ll the documents in a zip folder on the moodle page.
|  | Project DUE DATE: MR HSIUNG DOESN’T SHOW UP! Shayan and Moeen and Mellissa work on UML Diagrams while Amil and Ramie test for bugs. | We just realize we haven't even commented the code yet. We comment the code we made, and leave the complex code to be commented by Ramie. | We realised equipment panel doesn't work (Amil and Shayan) worked on it. It gets to the final stages but doesn’t save properly. Ramie spends half the night and cant fix it. |  | ICS Exam is tomorrow: We all get together and finish the commenting, we leave the UML diagram for Mellissa to finish. Ramie tries to add a splash screen but it doesn't work, so we just study. |  | We talked to Mellissa today and she had VS2008, the project file we sent her for UML was VS2010. So she is doing the UML diagrams and will send them to us soon.
| 2012-01-29 | 2012-01-30 | 2012-01-31 | Notes:
[5 empty] | Future Month Calendars: |  | Feb 2012 |  | Mar 2012 |  | Apr 2012
Created with WinCalendar Calendar Maker
► For more layouts, colors, options & for calendars with Holidays (for 10 Countries + Christian, Jewish & Muslim) download WinCalendar from WinCalendar.com.
► You can even import Microsoft Outlook & Google Calendar appointment data onto created calendars using WinCalendar.
► WinCalendar is also a integrated Windows, Word & Excel popup calendar that supports storing of daily appointments that display on created calendars.